## Sheet1
| Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Research data-analysis libraries in Python to inform the most suitable choice for our Obscurity Engine. | bar: Week 0
Research front-end frameworks (Vue.js, React, Angular, etc.) to inform the most suitable choice. | bar: Week 0
Research uses for ML in the Obscurity Engine to inform the most suitable choice for its potential inclusion. | bar: Week 0
Research database frameworks (MySQL, PostgreSQL, MongoDB, SQLite, etc.) to inform the most suitable choice. | bar: Week 0
Research platforms on which to host the database (Azure, AWS, etc.) to inform the most suitable choice. | bar: Week 0
Collect parameters for the Obscurity Engine (i.e., relevant metrics the engine should compute over). | bar: Week 0
Collect options for sport-statistics APIs and weigh them against the alternative of web scraping. | bar: Week 1
Guide discussion of weights on Obscurity Engine parameters (e.g., social following versus on-field statistics). | bar: Week 1
Design the UI/UX with a sequence of mockups representing state transitions. | bar: Week 1
Design the "Athlete DB" with Entity Relationship Diagrams. | bar: Week 2
Create Obscurity Engine | bar: Week 2 to Week 4
Create database tables with the chosen framework, on the chosen platform. Populate them with test data. | bar: Week 3
Tune the Obscurity Engine based on its response to predetermined test cases. | bar: Week 5 to Week 6
Tune standardization factors for our metrics across different countries, sports, leagues, etc. | bar: Week 5 to Week 6
Tune the Score Converter to produce digestible outputs for players of our game. | bar: Week 5 to Week 6
Develop the front end, per the mockups approved in the previous task, and vet it with test data. | bar: Week 4 to Week 5
Connect the front end to backend processes like the Query Manager, Guess Validator, Obscurity Engine, etc. | bar: Week 6
Decompose natural language questions into manageable logic for the Question Validator. | bar: Week 7 to Week 8
Refine the desired system operations during gameplay (i.e., the I/O through system components). | bar: Week 7
Tune the threshold of the Question Validator so that only questions of reasonable difficulty are pushed to the database. | bar: Week 9
Work on Final Presentation
Research: Research required tooling and conceptual background
Data Collection/Data Preproccessing: Collect required data from various sources and determine those sources
Frontend: Create a frontend interface for user interaction with gameplay
Database Development: Design and create database logic and infastructure
Obscurity Engine: Develop and tune the obscurity engine algorithmn
Question Validation: Develop a way to validate potential prompts and answers submitted
Final Presentation